## Sheet1
Week number
|  | Lead team member | Due date | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47
Work Package (WP) / Deliverable (D)/ Task (T)
WP1 | Literature review | BVL | 2022-09-10
T1.1 | Data modelling literature | HL
T1.2 | Data governance | EV
WP2 | Data collection | EV | 2022-09-18
D2.1 | LiDAR data | HL
D2.2
WP3 | Coding | HL | 2022-09-30
D3.1 | Coding 1 | EV
D3.2 | Coding 2 | BVL
WP4 | Dissemination and communication | BVL | 2022-11-24
D4.1 | Reporting | HL | [9 empty] | 2022-11-04 | 2022-11-10
D4.2 | Meetings | EV
WP5 | Management and Coordination | EV | 2022-11-11
| Coordination | HL
Deliverables
Activity